## Sheet1
Task | Start Date | End Date | Department | Project Type | Resource | Resource Manager
a | 2025-07-01 | 2025-07-06 | Systems | Retrofit | Oz | King
b | 2025-07-03 | 2025-07-06 | IT | Retrofit | Charlie | Queen
c | 2025-07-06 | 2025-07-10 | Systems | Field | Oz | King
d | 2025-07-07 | 2025-07-21 | Systems | Field | Oz | King
e | 2025-07-10 | 2025-07-24 | IT | Intervention | OZ | Queen
f | 2025-07-06 | 2025-07-12 | IT | Retrofit | Oz | Queen
g | 2025-07-02 | 2025-07-08 | Systems | Field | Beta | King

## Sheet3
Plant | Project Name | Project Type | Project Status | SE | SE Manager | FSP /FTP | Project Submitted Date | Start Date | End Date | Project Number
JAX | JAX Additional 3PL | 1PL | Pending Approval | Roberto Tactuk | Julian Gastelum
KC2 | KC2 Dynamic Tilt Functionality Fix | Ad Hoc | Pending Approval | Kiyara Hill | Ishan Arora
LAN | LAN ATU Kit Addition for DA2 L5 WIP | Ad Hoc | Pending Approval | German Estrada-Gutierrez | Julian Gastelum | 2025-06-09 | 2025-06-09 | 2026-03-02 | 2026-05-01
OKC | OKC Shipping Gaylord with LGV | Ad Hoc | Pending Approval |  |  |  |  | 2026-01-05 | 2026-03-27
BLM | BLM Check In lane expansion | Check in Lane Expansion | Pending Approval |  | Gregory Seyfried |  |  |  |  | 2923
RCH | RCH RCH Check-In Lane: Project Planning Phase | Check in Lane Expansion | Pending Approval | [6 empty] | 2923
KEN | KEN KEN -LAYOUT OPTIMIZATION | Layout Modification | Pending Approval | Roberto Tactuk | Julian Gastelum |  |  | 2025-10-06 | 2026-04-24
MIL | MIL L3 (Aluminum Line) | Line Additions | Pending Approval
HAZ | HAZ Layout Opt. (Removal PBC) | Opt | Pending Approval | Mohammad Karlawala | Gregory Seyfried |  |  | 2025-09-15 | 2025-12-19 | 0
JAX | JAX Layout Opt. (Removal PBC) | Opt | Pending Approval |  | Gregory Seyfried |  |  |  |  | 0
RIA | RIA Layout Optimization | Opt | Pending Approval | Victor Arrizon | Julian Gastelum |  | 2025-11-03 | 2026-04-24
HAZ | HAZ Implementation of Embedded | Software Enhancement | Pending Approval |  |  |  |  | 2025-09-15
TEM | TEM E80 Reach Optimization (Multiple sites but starting in TEM) | Software Enhancement | Pending Approval |  |  |  |  | 2025-11-03
NIA | NIA weight Segregation roll out | Software Enhancement | Pending Approval |  |  |  |  | 2025-09-08 | 2025-11-28
CIN | CIN S.M.I.L.E E80 | Software Update | Pending Approval | Osvaldo Cortes | Henry Martinez | 2025-04-10 |  | 2025-04-10 | 2025-11-28
JAX | JAX Ambient Room Automation | Software Update | Pending Approval | Yusuf Benton | Gregory Seyfried
NIA | NIA MA Cloud Development | Software Update | Pending Approval |  |  |  |  | 2025-01-13 | 2025-11-28
ST4 | ST4 Triple Stack | Triple Stack | Pending Approval |  | Ishan Arora |  |  | 2025-02-10 | 2025-02-21 | 0
JAX | JAX Dual Pallet Drive- In Racking | Layout Mod | Pending Approval | Yusuf Benton | Gregory Seyfried |  |  | 2025-09-15 | 2025-12-26
LOU | LOU Layout Optimization | Opt | Pending Approval |  |  | 2026-01-05 | 2026-04-24
NIA | NIA LGV Sensor Obsolescence | Software Enhancement | Pending Approval | Jason rodriguez | Julian Gastelum |  |  | 2025-09-15 | 2026-04-24
NIA | NIA LGV Sensor Obsolescence | Software Enhancement | Pending Approval | Jason rodriguez | Julian Gastelum |  |  | 2025-09-15 | 2026-04-24
NIA | NIA LGV Safety Campaign | Safety | Pending Approval | Mohammad Karlawala | Gregory Seyfried |  |  | 2025-08-04 | 2025-12-26
ST4 | ST4 Dual pallet Drive- in Racking | Layout Mod | Pending Approval |  |  |  |  | 2025-11-03 | 2026-02-27
NIA | NIA R&D Sensor Retrofit Roll out - 1 | Software Enhancement | Pending Approval | Cole Pellegrini | Ishan Arora |  |  | 2025-11-10 | 2026-12-25
NIA | NIA R&D Sensor Retrofit Roll out - 2 | Software Enhancement | Pending Approval | Cole Pellegrini | Ishan Arora |  |  | 2025-11-10 | 2026-12-25
DAL | DAL LGV Conversion | Retrofit | Pending Approval |  |  |  |  | 9/726 | 2027-02-26
NIA | NIA VP Line Optimization Roll Out | Software Enhancement | Pending Approval |  |  |  |  | 2025-09-15 | 2026-03-27
NIA | NIA VP Line Additiona (Line in a box) | Software Enhancement | Pending Approval |  |  |  |  | 2025-11-03 | 2026-04-17
ST3 | ST3 1PL | 1PL | Active | Osvaldo Cortes | Henry Martinez | NA | 2024-01-01 | 2024-06-11 | 2025-05-30 | 2710
BAY | BAY 3HX Exit (2 LGVs/ 3 ATU kits) | Ad Hoc | Active | Ricardo Garcia | Henry Martinez | 2025-05-19 |  | 2025-05-19 | 2025-06-13
KC2 | KC2 KC2 Injection Tote Automation | Ad Hoc | Active | Yusuf Benton | Gregory Seyfried |  |  | 2026-01-05 | 2026-03-20
LAN | LAN Layout Opt. (PBC Removal) | Ad Hoc | Active | German Estrada-Gutierrez | Julian Gastelum | N/A | 2025-05-02 | 2025-11-10 | 2026-01-30
MXC | MXC Shipping Optimization | Ad Hoc | Active | Kiyara Hill | Ishan Arora | N/A |  | 2025-05-12
NIA | NIA CGR03544 NIA - WIP Pallets Modification | Ad Hoc | Active | Osvaldo Cortes | Henry Martinez | 2025-08-25 | 2025-05-01 | 2024-11-04 | 2025-09-05
NIA | NIA Monthly SE KPI | Ad Hoc | Active | Osvaldo Cortes | Henry Martinez | NA | 2025-01-01 | 2025-01-01 | 2025-12-31
NIA | NIA 0 LGV Alarms | Ad Hoc | Active | Cole Pellegrini | Ishan Arora | 2025-04-28 | 2025-02-03 | 2025-04-28 | 2025-05-23
NIA | NIA Master NIA OIL List | Ad Hoc | Active | Osvaldo Cortes | Henry Martinez |  |  | 2025-01-01 | 2025-12-31
CIN | CIN BTS L1 - L3 | BTS | Active | Kayden Colby | Gregory Seyfried | 2026-02-20 | 2025-01-27 | 2026-01-05 | 2026-05-08
GDL | GDL BTS | BTS | Active | Gilberto Perez | Alvaro Eugenio Cantu | 2025-04-22 | 2023-10-31 | 2025-02-24 | 2025-06-27 | 3376
MIN | MIN BTS | BTS | Active | Adam Hoover | Gregory Seyfried | 2025-03-28 | 2024-09-02 | 2024-10-21 | 2025-06-27 | 2882
RCH | RCH Check in lane Expansion | Check in Lane Expansion | Active | Kayden Colby | Gregory Seyfried | 2024-11-15 | 2024-09-16 | 2025-03-10 | 2025-04-30 | 2923
RIA | RIA Check in lane Expansion | Check in Lane Expansion | Active | Osvaldo Cortes | Henry Martinez |  | 2024-09-30 | 2025-03-01 | 2025-11-28 | 2923
MIA | MIA Project Completion/Original Layout | Concrete Repair | Active | Yusuf Benton | Gregory Seyfried |  |  | 2025-01-21 | 2025-01-31 | MRO
COL | COL Dock Retro Commissioning | Dock retro Fit | Active | Roberto Tactuk | Julian Gastelum | 2025-05-21 |  | 2025-05-12 | 2025-07-04 | 3563
KC2 | KC2 Additional Mass Handoff | Layout Modification | Active | Kiyara Hill | Ishan Arora |  | 2024-11-04
CAR | CAR Adjusting Locations For Taller Pallets | Layout Modification | Active | Kiyara Hill | Ishan Arora | N/A | 2025-04-28 | 2025-05-02
PLA | PLA Layout Modification | Layout Modification | Active | German Estrada-Gutierrez | Julian Gastelum | 2025-04-28 | 2024-11-04 | 2025-04-28 | 2025-06-20
DA2 | DA2 L5 CSD | Line Additions | Active | Ricardo Garcia | Henry Martinez | 2026-04-01 |  | 2026-03-02 | 2026-05-08
GDL | GDL L2 .L3 | Line Additions | Active | Gilberto Perez | Alvaro Eugenio Cantu | 2025-11-21 | 2025-04-29
HOU | HOU Peason Palletizer | Line Additions | Active | Ricardo Garcia | Henry Martinez | N/A | 2024-10-14 | 2024-11-04 | 2025-05-16
JAX | JAX L6 GAL with Dual Pallet Racking + L7 | Line Additions | Active | Yusuf Benton | Gregory Seyfried | 2025-03-18 | 2023-10-31 | 2024-06-03 | 2025-07-11 | 3265
KC2 | KC2 L2 Expansion | Line Additions | Active | Jacob Doerksen | Henry Martinez | 2025-07-07 | 2025-02-03 | 2025-07-07 | 2025-07-11
LAN | LAN L6 (VP) | Line Additions | Active | Jason rodriguez | Julian Gastelum | 2024-08-13 | 2023-10-31 | 2025-09-01 | 2025-10-06 | 3260
LAN | LAN L4 WIP | Line Additions | Active | Jason rodriguez | Julian Gastelum | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-10-03
LAN | LAN L5 | Line Additions | Active | Jason rodriguez | Julian Gastelum | 2025-06-03 | 2025-06-03 | 2025-04-01 | 2025-06-27
LAN | LAN L3 WIP Palletizer | Line Additions | Active | Jason rodriguez | Julian Gastelum | 2025-09-30 | 2025-09-30 | 2025-08-18 | 2025-10-31
MES | MES L3 | Line Additions | Active | Victor Arrizon | Henry Martinez | 2025-04-25 | 2024-10-31 | 2025-02-03 | 2025-06-13 | 3008
MIN | MIN L3 Precon | Line Additions | Active | Adam Hoover | Gregory Seyfried | 2025-12-12 | 2025-05-28 | 2025-07-14 | 2026-03-13
MXC | MXC L3 | Line Additions | Active | Gilberto Perez | Alvaro Eugenio Cantu | 2025-04-08 | 2024-02-13 | 2025-02-17 | 2025-05-23 | 3371
ST3 | ST3 L3 GAL | Line Additions | Active | Jacob Doerksen | Henry Martinez | 2025-02-15 | 2024-09-16 | 2025-01-27 | 2025-06-06 | 3244
ST3 | ST3 Gallon Handle | Line Additions | Active | Jacob Doerksen | Henry Martinez | 2025-08-18 | 2025-06-16 | 2025-08-18 | 2025-08-29
TEM | TEM L4 Precon | Line Additions | Active | Ricardo Garcia | Henry Martinez | 2025-09-05 | 2023-10-31 | 2025-05-06 | 2025-08-17 | 3346
NIA | NIA Niagara Eye | Niagara Eye | Active | Jacob Doerksen | Henry Martinez | N/A | 2024-08-20 | 2024-08-05 | 2025-12-31
BLM | BLM Optimization | Opt | Active | IGAL CASCOE | Ishan Arora | 2025-04-15 | 2025-03-31 | 2025-04-21 | 2025-06-27
NOR | NOR Optimization | Opt | Active | IGAL CASCOE | Ishan Arora | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-05-19
PHI | PHI Racking | Racking Addition | Active | Osvaldo Cortes | Henry Martinez | NA | 2024-09-30 | 2024-12-10 | 2025-06-20 | 3024
NIA | NIA E80 Customer Service | Retrofit | Active | Osvaldo Cortes | Oscar Pinto | NA | 2025-01-01 | 2025-01-01 | 2025-12-31
RIA | RIA Pallet Inspection System | Retrofit | Active | Cole Pellegrini | Ishan Arora | 2025-10-21 | 2025-04-07 | 2025-10-20 | 2026-11-06
BAL | BAL Safety V2 (Last 5) | Safety | Active | Mohammad Karlawala | Gregory Seyfried | 2025-06-09 | 2024-07-15 | 2025-06-09 | 2025-06-13
LAS | LAS Safety V2 (Last 5) | Safety | Active | Mohammad Karlawala | Gregory Seyfried | 2025-06-02 | 2024-07-15 | 2025-06-02 | 2025-06-06
MOR | MOR Safety V2 (Last 5) | Safety | Active | Mohammad Karlawala | Gregory Seyfried | 2025-06-02 | 2024-07-15 | 2025-06-02 | 2025-06-06
NIA | NIA Safety PPDC | Safety | Active | Mohammad Karlawala | Gregory Seyfried |  | 2024-10-03
BAK | BAK 18 Min Load times | Software Enhancement | Active | Cole Pellegrini | Ishan Arora | 2025-07-07 | 2025-07-07 | 2025-07-07 | 2025-07-14
BAL | BAL Rack Putaway Optimization for Pallet Height | Software Enhancement | Active | Kiyara Hill | Ishan Arora | N/A | 2025-03-27
MIN | MIN FTL/TSL WaitPreStaging Start | Software Update | Active | Adam Hoover | Ishan Arora
NIA | NIA Network Wide AutoHSK Revision | Software Update | Active | Cole Pellegrini | Ishan Arora
RIA | RIA Single Pallet Pick Up - FIP FIP Remote Deployment | Software Update | Active | Cole Pellegrini | Ishan Arora | 2025-07-22 | 2024-11-04 | 2025-07-21 | 2025-07-25
NIA | NIA SE Project Resource Management | Support | Active | Osvaldo Cortes | Oscar Pinto | NA | 2025-01-01 | 2025-01-01 | 2025-12-31
NIA | NIA E80 PC Priority Sheet | Support | Active | Osvaldo Cortes | Oscar Pinto | NA | 2025-01-01 | 2025-01-01 | 2025-12-31
NIA | NIA NIA Top 10 | Support | Active | Osvaldo Cortes | Oscar Pinto | NA | 2025-01-01 | 2025-01-01 | 2025-12-31
NIA | NIA FD Matrix | Support | Active | Osvaldo Cortes | Oscar Pinto | NA | 2025-01-01 | 2025-01-01 | 2025-12-31
HAZ | HAZ Variety Pack Standarization | VP Standardization | Active | Roger Tran | Ishan Arora | 2025-07-14 | 2025-01-06 | 2025-09-15 | 2026-03-27
JAX | JAX Variety Pack Standarization | VP Standardization | Active | Roger Tran | Ishan Arora | 2025-08-11 | 2025-01-06 | 2025-07-14 | 2025-09-19
LAN | LAN Variety Pack Standarization | VP Standardization | Active | Roger Tran | Ishan Arora | 2025-09-15 | 2025-01-06 | 2025-08-11 | 2025-10-17
LOU | LOU Variety Pack Standarization | VP Standardization | Active | Roger Tran | Ishan Arora | 2025-10-13 | 2025-01-06 | 2025-09-15 | 2025-11-21
RIA | RIA Variety Pack Standarization | VP Standardization | Active | Roger Tran | Ishan Arora | 2025-06-09 | 2025-01-06 | 2025-01-06 | 2025-07-18
LAN | LAN Raw Material Segregation on Racks | Weight Segregation on racks | Active | Jason rodriguez | Julian Gastelum | 2024-11-20 | 2024-11-20 | 2025-07-21 | 2025-07-25
DA2 | DA2 L4 (GAL) + Building Expansion | Building Expansion | Active | Roberto Tactuk | Julian Gastelum | 2025-04-10 | 2024-02-22 | 2025-02-17 | 2025-05-16 | 3364
MIN | MIN L3 | Line Additions | Active | Adam Hoover | Gregory Seyfried | 2025-12-12 | 2025-11-17 | 2026-03-20
TEM | TEM L4 | Line Additions | Active | Ricardo Garcia | Henry Martinez | 2025-09-05 |  | 2025-08-18 | 2025-12-05
HAZ | HAZ Safety V1 (First 6) | Safety | Complete | Taher Poonawala | Henry Martinez | 2024-07-08 |  | 2024-07-08 | 2024-07-12
TEST | test | test | Active | Osvaldo Cortes | Henry Martinez |  |  | 2025-01-05 | 2025-01-10
Another | test | test | Active | Osvaldo Cortes | Henry Martinez |  |  | 2025-02-05 | 2025-03-10